# OER redesign milestone planner

Use this planner to organize an OER course redesign, on your own or with a team. The full OER Self-Directed Redesign course is optional.

## How to use this planner

Save a copy for your course. Use the example on page 2 to choose your own review dates.

For each checkpoint, name who will do the work and what you will review. Working alone? Put your own name and invite feedback if helpful.

At each checkpoint, record what is ready, what needs work, and who will do what next.

Adjust the plan as needed. The timing and support sessions on page 2 are suggestions.

Course: __________________________  Person leading the work: __________________

Support/review contact, if available: ________________________________________

## Your working milestone plan

| Checkpoint | Evidence to review | Local plan |
| --- | --- | --- |
| 1. Goals and alignment | Measurable objectives connected to assessments and learning activities. | Owner: __________ Date: ______ Decision / next action: __________ |
| 2. Materials and structure | Selected OER and reuse terms; Instructional Materials Plan and Course Alignment Worksheet. | Owner: __________ Date: ______ Decision / next action: __________ |
| 3. First chapter/module | One built sample reviewed for content accuracy, alignment, navigation and accessibility. | Owner: __________ Date: ______ Decision / next action: __________ |
| 4. Development check | Agreed course components built; remaining questions and accessibility issues assigned. | Owner: __________ Date: ______ Decision / next action: __________ |
| 5. Course review and revision | Course Review Checklist, feedback from others if available, and needed revisions. | Owner: __________ Date: ______ Decision / next action: __________ |
| 6. Implementation and maintenance | Course ready to teach; plan for student feedback and future updates. | Owner: __________ Date: ______ Decision / next action: __________ |

# Example timeline and support sessions

This seven-month example can be shortened or extended. Start Month 1 whenever your project begins. Course references are optional and refer to OER Self-Directed Redesign.

| When | Work to complete | Optional course reference |
| --- | --- | --- |
| Month 1 | Define course goals, measurable objectives and how learning will be assessed. | Getting Started and Modules 1–2 |
| Month 2 | Plan learning activities, select OER and complete the materials plan and alignment worksheet. | Modules 3–5 |
| Month 3 | Build and review one sample module. Establish navigation and adapt selected OER. | Planning to Build and Modules 6–7 |
| Month 4 | Improve accessibility, inclusion and presentation of content. | Modules 8–9 |
| Month 5 | Develop assessments and opportunities for interaction. | Modules 10–11 |
| Month 6 | Complete communication, instructor information and course welcome materials. | Modules 12–13 |
| Month 7 | Review the course, make revisions and prepare to teach. | Module 14 |

## Support session examples

Use these as team workshops, consultations or individual work sessions. These are examples to arrange locally, not scheduled events.

Getting started. Agree on scope, roles, timing and review criteria at the beginning.

OER selection and alignment. Review materials and their connections to objectives, activities and assessments near the end of Month 2.

Course building and media. During Months 3–4, work on LMS page formatting, accessibility, Canva layouts or reusable H5P activities as needed.

Preparing for review. At the end of Month 6, agree on who will review the course and what feedback would help.

Final revisions. During Month 7, address feedback and resolve remaining issues before teaching.